## Slide 1: SPE 102818 Успешное применение стратегии предотвращения факторов риска в процессе бурения скважин с большим отходом от вертикали при разработке проекта Одопту - Море, Сахалин
Н. Мохаммед, SPE, М. Чернов и
Е. Маналак-Троан, Шлюмберже
И. Кайдалов и В. Любушкин, Роснефть Сахалинморнефтегаз
Секция SPE, Москва, 14 декабря 06
SPE –Moscow, 14 Dec. 06
SPE 102818 Focused Risk-Management Brings a Step-Change Improvement in Drilling Performance at Sakhalin’s Odoptu ERD Development
N. Mohammed, SPE, M. Chernov and
E. Mañalac-Trøan, Schlumberger
Y. Kaydalov and V. Lubushkin, Rosneft Sakhalinmorneftegas
Notes: Good afternoon – today I will be talking about well construction on the Odoptu ERD development on Sakhalin Island.
This paper focuses on the progress made through both the introduction of new technology and improvements in organizational capability.
I would also like to acknowledge the input and support of my co-authors at Schlumberger. Maxim, who has responsibility for delivering the risk management strategy we outline in this paper, is a local expert based in Yuzhno.
Most importantly the generous support of Rosneft Moscow and partnership of SMNG in Yuzhno has allowed us to present today.

## Slide 2: План
Введение по проекту разработки месторождения Одопту при помощи бурения скважин с БОВ
Изучение проблем возникающих при бурении
Проект стратегии управления рисками
Внедрение Управления Рисками при Бурении
Воздействие на буровые работы
Заключение и дальнейшие действия
Outline
  Odoptu ERD Project Introduction
Investigation of Drilling Problems
Design of Risk Management Strategy
Implementation of Drilling Risk Management
Operational Impact
Conclusions and Next Steps
Notes: After an introduction to the Odoptu project I will summarize an investigation into drilling problems in early 2005 which subsequently led to the design and implementation of a focused, fit-for-purpose drilling risk management process.
I will then review the key operational impacts for the project as a result of these changes in operational capability and finish with an overview of conclusions and next steps.

## Slide 3: Odoptu North Dome - ERD Well Layout Северный купол Одопту – план скважин с БОВ
Exploration Wells
1 km
North Pad
Северный куст
South Pad
Южный куст
Разведочные скважины
Notes: <number>
<footer>
<header>
07/28/26
Odoptu Morye is a Miocene-age hydro-carbon accumulation lying off the northern part of the east coast of Sakhalin island. Most, if not all of the field lies within ERD well range from beachside land locations. Dimensions are roughly 4km E/W by 12 km N/S with producing intervals at roughly 1500-1700m TVD. It lies at the northern end a group of fields including Chayvo, Piltun and Arkutun.
The field was discovered in 1977 while an extensive exploration drilling program was carried out in the 1970’s in this area. In fact the first ERD well – to 2.5km displacement - was drilled in 1973 and remained a record in Russia for the next 10 years.
Odoptu’s North Dome is operated directly by OJSC Rosneft-SMNG, a majority-owned production entity of Rosneft. The southern section of the field (not shown here) is due for development by XOM in the coming 2-3 years. The commercial extraction of oil began in 1998. 2005 production was in the region of 500,000 tons – 2006 production is expected to reach 800,000 tons.
To date 21 wells, with horizontal aspect ratios up to 4.1, have been drilled and completed from two land-based drilling locations which target the North Dome. First phase of development from the ‘North Pad’ began in 1998 with the drilling of 8 ERD wells.
Drilling began in late 2003 from a second location 5km to the south and, after 2 wells, Rotary Steerable Systems (RSS) were introduced to replace positive displacement motors (PDM). Presently, 11 wells have been drilled from this ‘South Pad’ and a second exploitation phase is underway on the North Pad.

## Slide 4: Профиль скважин – Вертикальный Разрез
Интервалы нестабильности Zones of Instability
Odoptu Well Profiles - Cross Section
Notes: <number>
<footer>
<header>
07/28/26
The Odoptu South Pad rig is an IRI E-2100 design with 400 ton skidable derrick, Canrig 1050 top-drive rated for 45000 klbft, and 3 Ideco T-1600 triplex pumps. Drillpipe inventory includes over 4000m of 5 ½” and 5000m of 6 5/8” drillpipe in addition to 5” pipe. It is worth noting that while this is a reasonably capable rig, it is now 10 years old and there has been little additional modification for ERD well drilling.
Standard geometry is 17 ½ x 12 ¼ x 8 ½” hole. Build rates range from 2 to 3.5 deg/30m and sail angles are roughly 75-82 deg. Reservoir sections are sub-horizontal, generally 300 to 600m long and are completed with a 6 5/8 or 7” cemented liner.
Top-hole casing (13 3/8” 61 lb/ft) most recently has been run to depths of 1900 m with sail inclinations of 78. Intermediate (9 5/8” 40 lb/ft) casing is floated to TD fully-evacuated at near-neutral buoyancy. Rotation is generally required on the lower third of the casing run, and running speeds are progressively reduced due to increasing hydraulic friction in the annulus. The longest run of 9 5/8” has been to 6446 m at a sail angle of 80-84 deg.
Mud is a 60/40 IOEM system with static density increasing from 1.12 sg in the top hole to 1.24 sg in the reservoir. Cuttings are treated and disposed of 20km from the rig location. Mud engineering is supplied through a division of SMNG.
Continuous back-reaming (string rotation and circulation) while pulling out of the hole has historically been the standard practice in larger (17 ½” and 12 ¼”) hole sizes. This is primarily due to pump and flow rate limitations at TD of these sections. Experience has shown that this level of mechanical assistance is necessary to ensure the hole is clean enough to run casing without circulation.
Apart from localized wellbore instability, the drilling risk regime is relatively benign for ERD operations. But these localized zones have proven to be the source of significant drilling NPT up to now. More about this later.

## Slide 5: Развитие показателей бурения на Одопту
Rotary Steerable Technology
Роторная Управляемая Система
Motor Technology
Технология ВЗД
Problem Well
Проблемная Скважина
Odoptu Drilling Performance Evolution
Wells
Notes: The 8 North Pad producers were drilled from 1998 to 2003 with positive displacement motor (PDM) technology. Drilling performance metrics reached a plateau of 2200m/month (gross) by the end of this phase (see figure 2). The learning curve trend was maintained for the first two wells on the South Pad while motor use was continued.
The introduction of rotary-steerable (RSS) technology saw a step-change improvement in gross progress rates (spud to liner TD) of 33% to 2900m/mth over the next 3 wells while per-meter costs increased marginally. In fact, net progress rates (exclusive of non-drilling NPT) in 12 ¼” and 8 ½” hole more than doubled.
Performance on the 6th North Pad well, however, indicates that the adoption of RSS technology, by itself, was not a guarantee of sustained performance improvement. In fact, this well (206) incurred a serious level of NPT due to well-bore instability while back-reaming in 12 ¼” hole and the rapid escalation of the resultant hole-cleaning problems while running 9 5/8” casing.
Tech improvements help with slant times, but process improvements are needed to help with flat times.

## Slide 6: Обломки пород из интервалов кавернозности
Debris from Cavity Zones
Description: Mudstone, hard, fine-grained structure.
Shape: Flat, Two sides almost parallel, size is up to 6 cm in diameter, 2 cm in height.
Описание: Аргиллит, плотная, мелкозернистая структура.
Форма: Плоская, две стороны почти параллельны, размер – до 6 см. в диаметре, 2 см в высоту.
Notes: <number>
<footer>
<header>
07/28/26
The experience of well 206 prompted an independent investigation to isolate the root cause of excessive NPT. Detailed review of drilling records showed that the large majority of symptoms (excessive torque/drag, ECD spiking, pack-offs and stuck pipe) were confined to relatively short depth ranges along-hole.
Eventually, as hole cleaning symptoms worsened, cubic meters of surplus returns were recovered from localized areas. These were described as hard mudstone with a fine-grained structure and dimensions of up to 6 cm in diameter and 2 cm in height.
The morphology of these returns is not clearly indicative of a classical shear-failure mechanism due to low mud weight. Given their localized nature in the well and the ability to correlate these zones across part of the field it is likely that the failure mechanism is related to some anisotropic property of the rock fabric itself.

## Slide 7: Данные исследований множественных прохождений (CDNI)
Survey package enters cavern heading down and left Выход из каверны Направление - вверх и вправо
Survey package enters cavern heading down and left Вхождение в каверну Направление - вниз и влево
Azimuth / Азимут
Зен.Угол
Multi-pass High-Res Survey Data (CDNI)
x6
Notes: <number>
<footer>
<header>
07/28/26
Finally, and crucially, analysis of real-time MWD data while back-reaming showed that localized rugose zones (cavities) could be inferred directly from anomalies in high-resolution multiple-pass survey information. This was essentially fully qualified survey data (CDNI – Continuous Direction and Inclination) acquired by the MWD tools on a continuous time-basis through previously drilled hole.
A set of multi-pass CDNI data is shown for part of well 206. The inflected curves clearly track survey package excursions of up to 1.5 deg from the as-drilled axis of the borehole while the MWD collar makes a number of axial traverses of the cavity. The following key inferences can be made:
There is an unambiguous indication of the axial extent of well-bore enlargement – ie. 3010 to 3060m.
There is an unambiguous indication of the TVD thickness of the enlargement zones - in this case 10m. (inclination around 75 deg)
The cavity deviation axis is down and to the left - not vertical.
Multiple passes of data indicate that cavity growth is time-dependent and mechanical disturbance (back-reaming and circulation) is accelerating the process.
It is likely that the well-bore immediately above and below the cavity is substantially in gauge.
Диаграмма схематически показывает границы каверны и показания CDNI (Последовательные данные угла и азимута в реальном времени при прохождении прибора телеметрии через каверну)
Желтые и красные линии показывают увеличение каверны при каждом новом СПО при проработке ствола.
Ось отклонения примерно 135 градусов на право – при классическом расширении вертикальное направление расширения

## Slide 8: Образования каверн на других скважинах
Incipient Cavities on Other Wells
x9
x9
x9
x9
Notes: <number>
<footer>
<header>
07/28/26
Similar examples are observed on most Odoptu wells in all hole sizes (figure 5). In fact, two rugosity signatures have been identified on back-reaming data;
1 - the inflection response of localized cavities with dimensions similar to the BHA length (30-50m along hole);
2 - elongated intervals of hole enlargement (100 to 300m along hole).
Cavities do not have to be well developed (ie. a significant drilling hazard) to be evident. Early-stage development is clearly visible with anomalies as small as 0.2 deg provided suitable quality data and transmission rates are available for CDNI. Cavity location and characteristics have also been substantiated in 8 ½” hole by caliper and image data from LWD porosity tools.

## Slide 9: Stuck-Pipe Mechanism in Cavity Zone
1 – initial trip - hole drilled through cavern prone area
1 – Первое долбление – ствол пробурен через кавернозную зону
2 – back-reaming trip, excessive borehole damage = cavity
2 - Проведение профилактического подъема с проработкой, повреждение ствола = каверна
3 – final trip – packed-off & stuck while back-reaming & pressure from below is energizing the blockage
3 – Достижение проектного забоя, проведение подъема с проработкой –скапливание шлама в стволе и прихват
Notes: <number>
<footer>
<header>
07/28/26
The availability and understanding of multiple-pass, high resolution CDNI data was instrumental in determining the primary cause-effect relationships between well bore instability and significant NPT on the 206 well.
Root cause of hole cleaning difficulties was the development of localized rugose zones (cavities) due to tripping/back reaming and the associated spreading of non-drilled debris from the these zones.
Mechanical disturbance primarily influences the rate of cavity development. Exposure-time and low mud weight are probably contributing as a secondary factors.
While tripping and back-reaming, the debris field competes for space with BHA pinch-points (stabilizers and bit) in gauge hole immediately above and below the cavities.
The escalating symptoms of hole-cleaning problems (excessive reaming, ECD spikes, pack-offs and stuck-pipe) are due to debris being concentrated in the hole next to the BHA pinch-points immediately above and below the cavity zones.
The pack-off is energized from below (trapped pressure) exacerbating the problem and destabilizing the hole below the cavity.
The care and attention that goes into detailed observation at the rig-site has been essential for a clear assessment of cause-effect relationships. It has also resulted in a cost-effective and efficient methodology for tracking the presence and development of cavities, despite the characteristically subtle signs accompanying their initial formation.

## Slide 10: BOW - TIE Risk Analysis
Cavity
Formation
Threat or Control EVENT Mitigation Hazard or
Escalation Strategy or Recovery Consequence
Hi-Res Time-Lapse Survey data (CDNI)
Proactive Backream Regime
Communication Program
Avoid Trips in known risk zones & minimize Tripping
Tool / Rig Reliability
Mechanical disturbance
Subtle Real-Time Indicators
Hole Size
Trip Count
Exposure Time
Well Orientation
Avalanche Cavings
45 – 65 (deg incl)
Debris / Cavings Beds
PACKOFF – ECD spike
PACKOFF – stuck pipe
Casing Set Off – Bottom
Casing Stuck off-bottom
New Casing Architecture
Optimized Backream Regime
Circulate Hole clean in identified non-risk zones
Jar DOWN with Torsion unless a non-caving mechanism is proven
Notes: <number>
<footer>
<header>
07/28/26
Identification of cavities as the root cause of drilling NPT on well 206 was a key step forward. Developing an understanding of their geomechanical characteristics remains important for minimizing longer-term project risks. However, the most critical requirement was to effectively improve drilling performance in the short-term. (PRESS)
A customized risk-management strategy for drilling operations was developed and refined for the wells following 206. Over a one or two well period this was eventually consolidated in the form of a BOW-TIE analysis, built around the key event of cavity formation. To be effective, Bow Tie analysis requires a high level of experience regarding drilling operations and the components that relate to drilling risk management. This can be a challenge, but done correctly, it makes for an appropriate framework for implementation.
A Bow-Tie Analysis is a well known risk assessment methodology, and was actually refined most recently in the oil industry for the study of safety cases for offshore platforms. Here it has been used document a systems approach to managing risks in the Odoptu drilling process.
A summary was made of the known threat factors for cavity formation, clearly prioritized through the understanding of the key event (itemize). This was followed by an inventory of post-cavity consequences (itemize). Then the experience of the drilling team was brought to bear on the identification and refinement of appropriate barrier strategies (itemize) to limit cavity formation. Finally mitigation options were defined to prevent the escalation of consequences (itemize).
A clear understanding of the Key Event is crucial to a successful risk management strategy.
From the FAA Website (do not read – this is background info on Bowtie Analysis):
The Bow-Tie Diagram is a structured approach to risk analysis within safety cases where quantification is not possible or desirable. It has evolved over the past decades from the Cause Consequence Diagram of the 1970s and the Barrier Diagram of the mid 1980s. The Bow Tie analysis technique was orignially conceived as a tool for studying safety cases in the oil and gas industry. By linking hazards and consequences through a series of event lines it is possible to develop a diagram illustrating the routes to accidents. On the diagram, preventive and recovery controls are illustrated to show the fundamental components of the safety management system. Further understanding is gained by examining the routes by which the controls can fail and identifying the critical components of the system that prevent these failures. The Bow-Tie process is composed of the following steps:
Identification of the top events with their hazards
Assessment all the potential threats and escalating factors
Identification of control measures to prevent the hazard being released
Identification of mitigation or recovery measures.
Advantages : 1) The graphical representation the bow tie diagram can give a clear picture of what are often complex safety management systems. 2) Clear links between management systems and safety are shown Disadvantages : 1) Bow Tie analysis requires a high level of knowledge regarding a system and the components of the system that relate to its safety 2) Training is required 3) It is difficult to link to quantitative techniques 4) It doesn’t use Boolean logic

## Slide 11: BOWTIE – Анализ рисков
Образование каверн
Факторы Стратегия Событие Смягчение Опасность и угрозы контроля или восстановление последствия
Данные по времени с высоким разрешением (CDNI)
Проактивный режим обратной проработки
Программа коммуникации
Избегать СПО в известных зонах риска и минимизировать СПО
Надёжность бур.установки / инструмента
Механические воздействия
Слабые индикаторы в реальном времени
Диаметр скважины
Количество СПО
Время воздействия
Ориентация скважины
Интервал активного оседания шлама
45 – 65 (угол наклона)
Наносы обломков и шлама по стволу
Закупрока затруба - сквачок ECD
Закупорка – прихват труб
Недопуск обсадной колонны до забоя
Прихват ОК выше забоя
Изменение конструкции скважины
Оптимизированный режим обратной прорпботки
Очистка ствола в выявленных безопасных зонах
Использование Яса и вращением если не доказан механизм образования каверн
Notes: <number>
<footer>
<header>
07/28/26
Russian version of previous slide.

## Slide 12: BOW - TIE Risk Analysis
Cavity
Formation
Threat or Control EVENT Mitigation Hazard or
Escalation Strategy or Recovery Consequence
Hi-Res Time-Lapse Survey data (CDNI)
Proactive Backream Regime
Clean with flow / not RPM
Confirm hole is clean prior to trips
Avoid Trips in known risk zones & minimize Tripping
GM modeling & refinement
Evolutionary Increase in MW
BHA design / planning
Tool / Rig Reliability
Communication Program
Minimize Pump Cycling
Hydraulics Management (APWD, drilling practices)
Upgrade Seismic
Shoe Design
Mechanical disturbance
Subtle Real-Time Indicators
Low Mud Weight
Well Orientation
Well Location
Trip Count
Exposure Time
Team Awareness
Hole Size
Hydraulic Shock
Fault Regime
Avalanche Cavings
45 – 65 (deg incl)
Debris / Cavings Beds
PACKOFF – ECD spike
PACKOFF – stuck pipe
Excessive NPT
Casing Set Off - Bottom
Casing Stuck
Loss of Hole Section
Loss of Well
New Casing Architecture
Optimized Backream Regime
Circulate Hole clean in identified non-risk zones
Increase MW
Jar DOWN with Torsion unless a non-caving mechanism is proven
Flexible Shoe Depth
Sidetrack
Notes: <number>
<footer>
<header>
07/28/26
This slide shows a more complete set of factors but is harder to read. Here the priority items in red (included on the previous slide) highlight the key focus areas of the drilling risk management strategy for Odoptu.
It has been found that this approach is quite cost-effective – it does not cost a lot of money and, properly implemented, brings disproportionate amount of value. The main limitation on success is the proactive support of management. Universal buy-in was difficult to achieve in the early stages of the program but it has presently been in continuous use for more than a year on the South Pad. It has also been extended to drilling operations on the North Pad.
Note that there are relatively few contingencies and a relative preponderance of control measures – this is a clear reflection of the fact that prevention measures are relatively easy to define once the true nature of the problem is understood by experienced people. The lack of contingency measures reflects the (actually experienced) fact that the cavern, once initiated, can escalate to a fairly high consequence outcome very quickly.

## Slide 13: BOWTIE – Анализ рисков
Образование каверн
Данные по времени с высоким разрешением (CDNI)
Проактивный режим обратной обработки
Clean with flow / not RPM
Подтверждение чистоты ствола перед СПО
Избегать СПО в известных зонах риска и минимизировать СПО
Моделирование геомеханики
Эволюционное увеличение веса БР
Проект КНБК / планирование
Надёжность установки / иструмента
Программа коммуникации
Минимизировать циклы работы насоса
Управление гидравликой (затрубное давление, опыт бурения)
Улучшенная сейсмика
Дизайн башмака
Механические воздействия
Слабые индикаторы в реальном времени
Низкий вес БР
Ориентация скважины
Расположение скважины
Количество СПО
Время воздействия
Осведомлённость персонала
Диаметр сважины
Гидровлический
удар
Разломы
Обрушения/осыпания
45 – 65 (угол наклона)
Обломки / Осыпания
Закупорка – скачок ECD
Закупорка – прихват труб
Избыточное непродуктивное время
Установка ОК выше забоя
Прихват ОК
Потеря секции
Потеря скважины
Новая конструкция обсадной колонны
Оптимизироанный режим обратной проработки
Очистка ствола в выявленных безопасных зонах
Увеличение веса БР
Использование яса и вращения если не доказан механизм образования каверн
Изменение глубины посадки башмака при необходимости
Боковой ствол
Факторы Стратегия Событие Смягчение Опасность и угрозы контроля или восстановление последствия
Notes: <number>
<footer>
<header>
07/28/26
Russian version of previous slide

## Slide 14: Протокол управления рисками для буровой
Stratigraphy (MD and TVD)
Стратиграфия (MD и TVD)
Геомеханическая модель и прогнозируемые кавернозные зоны
Geomechanical Model and Prognosed Cavity Zones
Risk Assesment and Management Strategy
Оценка рисков и стратегия их управления
Previous Lessons Learned Усвоенные уроки
Risk Management Protocol for the Rigsite
x9
Notes: Just as important as the development of a customized risk-management strategy was the requirement for a reliable, sustainable method of implementation. The rig-centric approach used on Odoptu has been practiced for several years, notably in the North Sea, Gulf of Mexico and South America.
The main planning tool of this approach is essentially a collective document, which we call a DRILLMAP, (PRESS) classifying depth-referenced drilling risks and detailing control/contingency measures against the backdrop of the mechanical earth model (or MEM). Critical event symptoms are demonstrated with examples.
A new version of the protocol (along with the MEM) is created for each well. This is a rigsite tool with the detail necessary for the rig team to effectively put into practice the risk-management guidelines developed during the planning stage for each well.
Though it is too small to show details I will briefly summarize the contents of this document:
First section is a stratigraphic summary of the entire overburden and reservoir, by TVD and MD
Second section summarizes an along-hole (1 dimensional) Geomechanical Earth Model or MEM. This is currently used to provide a classic well-bore stability perspective while highlighting the cavity prone areas.
Third section gives detailed instructions for drilling risk management specific to the well. The BOWTIE framework is used to guide the thinking for both preventative and mitigation measures. A risk ranking, classified under the broader categories of loss/gain, wellbore instability, stuck pipe and hole-cleaning is also given.
Fourth section provides a series of examples summarizing lessons and strategies from previous wells as a ready reminder to the rig team.

## Slide 15: Организационная структура управления рисками
Rosneft Burenie(formerly part of SMNG)
Nogliki
Роснефть Бурение(в прошлом часть СМНГ)
Ноглики.
Schlumberger
D&M FSM
Yuzhno-Sakhalinsk
Шлюмберже
D&M FSM
Южно-Сахалинск
Geomechanics
Specialist
Специалист по
геомеханике
Drilling Specialist
Technology Hub
Moscow
Эксперт по бурению
Центр Тенх. Эксперт.
Москва
PERFORM Engineer
Odoptu / Yuzhno
Инженер PERFORM
Одопту / Южно-Сах.
Rosneft SMNG
Geology Department
Yuzhno-Sakhalinsk
Роснефть СМНГ
Отдел геологии
Южно-Сахалинск
Rosneft SMNG
Drilling Department
Yuzhno-Sakhalinsk
Роснефть СМНГ
Отдел бурения
Южно-Сахалинск
Rosneft Burenie
Rig Site - Odoptu
Рофнефть Бурение
Буровая - Одопту
Клиент < - - - > Сервисная компания
Planning / Contingency / Peer Team
Real – Time support
Evaluation (learning / after – action)
Планирование
Поддержка в реальном времени (24-7)
Оценка (изучение / последствия)
Client < - - - > Service Co
Risk Management Organization
Notes: <number>
<footer>
<header>
07/28/26
Currently, the rigsite team includes a dedicated engineer as the owner of this tuned, pro-active risk management strategy while drilling. This is a central role with direct links to the drilling contractor, operator’s leadership group and peer/oversight personnel in the service organizations.
During execution of the well a daily status report, catered to upcoming operations, is delivered to key stakeholders. This includes an update for a number of customized on-going surveillance and analysis initiatives, and re-iterates in detail the barriers and contingency measures necessary for the day. A peer-reviewed report is provided after each well to capture and incorporate lessons-learned for planning of the next well.
The pivotal success factor has been the presence of a dedicated and empowered custodian of the risk-management strategy at the rigsite. The presence of this individual ensures the delivery of effective engineering solutions integrated with real-time measurements. This results in good quality decision-support to optimize drilling efficiency, and continuous risk evaluation for minimized NPT.
In effect this individual (we call him a PERFORM engineer) needs to communicate on a regular basis with 3 client structures.
SMNG drilling department in Yuzhno
Rosneft Burenie (drilling contractor) management in Nogliki (North Sakhalin)
Rosneft Burenie (drilling contractor) operations at Okha (rigsite)
Odoptu
Of course he/she also has access to internal Schlumberger resources such as Geomchanical and Drilling Engineering expertise for peer review, as well as the corporate knowledge base (or communites of practice) from other PERFORM operations.

## Slide 16: Воздействие на операции
  Innovative, cost-effective use of CDNI data.
  Dynamically determined casing shoe depths.
  17 ½” hole to 1900m at sail angle of 78 deg.
  Pro-active back-reaming control to limit pack-off.
  Dynamic T&D models of drilling/casing ops.
Successful run of deep 95/8” causing Успешный спуск ОК диаметром 9 5/8” in the cavity prone area of the field. в кавернозном участке месторождения
  Инновационное, эффективное использование данных CDNI.
  Динамически определяемые глубины башмака обсадной колонны.
  17 ½” секция с наклоном в 78 градусов до глубины 1900м.
  Проактивный контроль (ECD) эквивалентной циркуляции плотности для предотвращения закупорок затруба.
  Моделирование нагрузок и крутящего момента при бурении и спуске обсадных колонн
Operational Impact
Notes: Here we have a summary of the key impacts this approach has facilitated.
CDNI data is used to give unambiguous early warning to to the presence of cavities.
Casing architecture is driven by a dynamic understanding of the precise location and condition of the cavities.
Deep 9 5/8” casing architecture has been achieved on a longer well than 206, and very close by. This success is key for longer wells planned in the future for this project.
Related activities are in place tp monitor well-bore conditions and recommend appropriate action in timely fashion.
New casing architecture isolates cavities in two different hole sections – required to manange the risks of high inclination 17 ½” hole.

## Slide 17: Эволюция дизайна обсадной колонны
5239 м
5800 м
6888 м
Shallow 9 5/8” shoe as deep as possible
Глубина 12 1/4” секции до верхней
точки нижней кавернозной зоны
Увеличение глубины и сложности скважины
Two main cavity zones in one hole section
Две основных кавернозных зоны в одной секции
Deep 13 3/8” shoe as shallow as possible
Удлинение 17 ½” секция для перекрытия
верхнего проблемного интервала
Evolution of Casing Design
Increase in depth and well complexity
A
B
C
Notes: Evaluation of casing design to mitigate risks with hole instability
206 – 3 instability intervals in 12 ¼” section – highest NPT.
229 – short 9 5/8” design for short wells led to decreased cycle times. No NPT due to instability
219 – return to deep 9 5/8” casing design – cavities are managed individually in separate hole sections. Challenge to set high inclination 17 ½” hole so deep but it is managed through good ERD practice.
Background comments (do not read):
In the beginning of South Pad drilling operations was applied 3 casing design that assume: drilling of 17 ½” section build section approximately to 1200 m MD covering build interval with 13 3/8” casing, drilling tangent 12 ¼” section with 9 5/8” casing point set above reservoir approximately to 5000 m MD and 8 ½” horizontal section to the end of the well and then running the 7” (6 5/8”) production linear.
After drilling of 206 well and problems in unstable shale intervals along the 12 ¼” section was decided to change strategy for the next upcoming injection wells up to 5000-6000 m to 2 casing design with long 12 ¼” hole from 100 m to 2500 m MD and then to drill 8 ½” section up to 5880 m (229 well) with 6 5/8” casing run to TD.
Change in technology to 2 casing design brought a reduction in well building cycle (224, 226, 227, 229) allow to start optimization of technology on experience of 224 and 226 wells by changing of 9 5/8” casing set point to cover unstable intervals.
Drilling of 12 ¼” hole section to around 3000 m allowed to cover upper and lower unstable shale intervals with 9 5/8” casing, problems during POOH was encountered in upper interval but minor unstable interval was covered with less time exposure without any sign of instability during backreaming operations and casing runs.
On well 219 with increasing of planned hole depth up to 7000 m MD, was needed to return to 3 casing design used last time on 206 well.
Planned well trajectory TD was 6300 m MD. Planned casing design: 13 3/8” casing up to 1500 m MD, 9 5/8” casing to 5450 m and 6 5/8” production linear to TD of horizontal section.
Based on experience of previously drilled wells and correlation of unstable intervals with 206 well this plan suppose to leave cavity prone intervals in 12 ¼” section which could potentially cause repeat of events of 206 well: degradation of unstable intervals with time, destabilization of intervals during backreaming operations, problems with 9 5/8” casing run.
To optimize well design in order to mitigate this risk was decided to increase the depth of 17 ½” section to 1900 m and to set 13 3/8” casing right after upper unstable interval 900-950 m TVD, it would give less time exposure on upper unstable interval for cavities to appear, no cavity related problems during the 13 3/8” casing run, covering upper interval will still leave minor and lower proven cavity interval in 12 ¼” hole section but would make 12 ¼” section shorter, less cavity prone intervals, less cavings in hole, backreaming operations with a fewer problems, better 9 5/8” casing run. 9 5/8” casing set depth was based just on geological reasons before drilling horizontal production section.
Achieved Results: 17 1/2” section was drilled to 1900 m MD. Upper unstable interval 1470-1720 m MD (880-940 m TVD). After 1-2 days interval was drilled CDNI data during the backreaming showed enlargements of interval.
No problems were encountered during backreaming operations, 13 3/8” casing was run to TD filled with mud without problems.
On the picture xx. shown evaluation of well design from 206 well, location of unstable intervals and mitigation of known risks by setting 13 3/8” casing deeper.
1 ) 206 well, 3 casing design – all unstable intervals in 12 ¼” section
2) 227, 229 wells, 2 casing design – upper and minor interval in 12 ¼”
3) 219 well, 3 casing design – Upper interval is covered by 13 3/8” casing
For the next upcoming well on South Pad 13 3/8” casing would be approximately set to 2300 m MD according to the geological correlation with upper unstable interval.

## Slide 18: Well Construction -Chronology
C
Q1 2006
drilled successfully, Deep 9 5/8 design
1 квартал 2006
Успешно пробурена скважина
1 km
A
Q1 2005
Well drilled and sidetracked
1 квартал 2005г. Пробурена скв. с зарезкой бокового ствола
Intermediate casing design wells
промежуточные скважины
B
B
Строительство скважин - хронология
Notes: <number>
<footer>
<header>
07/28/26
Here is a brief overview of the chronology and location for well construction achievements described so far.
RED shows the location towards the southern end of the south pad.
ORANGE shows the location of intermediate wells
GREEN shows the location of the recently drilled long well

## Slide 19: Эволюция показателей бурения на Одопту
Rotary Steerable Technology
Роторная Управляемая Система
Drilling Risk Management
Управление рисками при бурении
Motor Technology
Технология ВЗД
Odoptu Drilling Performance Evolution
Wells
Notes: So we can now revisit our drilling performance evolution in a new light. After the experience of the 206 problem well we have developed organizational capability to make the next step in performance improvement. A sustainable program of focused risk management at the rigsite as allowed wells to be drilled safely in the same area of the field that has previously posed a severe problem.
It should be noted that no fundamental changes in technology have been introduced to make this change – it is only development in organizational capability and a structured approach to decision support.

## Slide 20: Стратегия Управление рисками
  A second step-change Второй сдвиг в in drilling performance показателях бурения
  Investigation to analyze cause-effect Исследование опыта relationships in the x6 experience скважины x6
  The development of a specific depth-based Разработка геомеханической geo-mechanical model for each well drilled модели для каждой скважины
  The preparation of a customized Подготовка стратегии по risk-management strategy for drilling operations управлению рисками для - built on the root-cause assessment буровых операций
  Planning / Contingencies / Incorporating Планирование / Выполнение/ Learnings Изучение
  The addition of real-time decision-support Надежное внедрение стратегии function at the rigsite to implement the strategy поддержки в реальном времени in a reliable and consistent manner. на скважине.
Customized Risk Management Approach
Notes: An investigation to determine the cause-effect relationships of this incident led to a number of planning and operational changes. The most significant of these included:
The development of a specific depth-based geo-mechanical model for each well drilled.
The temporary simplification of casing architecture to isolate key unstable zones in separate hole sections.
The preparation of a customized risk-management strategy for drilling operations that was built on the root-cause analysis of the 206 investigation.
The addition of a real-time decision-support engineering function at the rigsite to implement the risk-management strategy.
These efforts resulted in a second step-change in drilling performance for the wells subsequent to 206.

## Slide 21: Real – Time Decision Support (Yuzhno)
Notes: Previous slide mentions the introduction of the decision-support function at the rig. Since the paper has been published we have also got this capacity remotely from the rigsite operation.
This is an example of the collaboration process currently going on in Yuzhno to bring the operation closer to the key decision makers in the project. We are using this kind of software (proprietary) to monitor rig operations on a 24-7 basis in a so-called operations support center (OSC).
The small video shows the development of drilling parameters to sidetrack one of the Odoptu wells. At the time there were problems initiating the sidetrack and a decision was required on whether to pull out of the hole and change the BHA.
The data being viewed can be broken down into 4 areas (originally on two separate 19” screens):
1- right hand track shows time-based data in log format
2- next track to the left shows depth based data with a superposition of the drilling BHA in simultaneous fashion
3- upper left area shows time-based detail of drilling parameters in highly customizable format (like an electronic chart recorder) for the detailed examination of drilling events
4- lower left area is a collection of key drilling data in numeric format and can be used to set alarms (turns colours other than blue to indicate cautionary state of data).

## Slide 22: Центр поддержки решений в Ю.-Сахалинске
Забуривание ствола с роторной системой на 5650 м
Взаимодействие Ю.-Сахалинск
Взаимодействие Москва
Notes: This rig data was available to the offices both in Yuzhno and Moscow while the operation was going on. The rig team, of course, was already very familiar with the history of the operation but this display allowed the office personnel to quickly ‘catch up’ in order to review the problems and support the decision process. This panel in particular was useful to examine the time-based operation in some detail.
Problem was to achieve a sidetrack (or separation) of the two wellpaths by digging a new hole with the drillbit and rotary drilling steerable BHA. In this case there was some evidence that the lower side of the wellbore was not smooth enough to ensure the good sliding required for establishing the new wellpath.
The data shows the hook (or drillstring) position and the load on the bit as the driller repeats a number of attempts to establish a smooth reaming pattern on the lowside of the hole. After roughly 24 hours it was successful in this case.
The availability of this data in both Yuzhno and Moscow contributed to good decision support and saved a trip. The sidetrack was successfully achieved with this BHA.

## Slide 23: Забуривание ствола с последующей геонавигацией
Забуривание ствола роторной
системой на 5650 м
Sidetracking for Geosteered Horizontal Section
Openhole sidetrack with
Rotary Steerable at 5650m
Notes: <number>
<footer>
<header>
07/28/26
Here is a schematic to show the situation with the well at the time.
Red wellpath was actual drilled pilot hole to determine reservoir thickness. Blue wellpath was the planned sidetrack to follow the expected reservoir profile with a geo-navigational approach. Sidetrack point is shown by the arrow.
This operation is not so straightforward to achieve in an ERD well. Particularly if the sidetrack depth range is limited. Success depends on well inclination, curvature, formation type and hardness, skill of (directional) driller.

## Slide 24: Заключение и дальнейшие действия
Conclusions
  Причиной нестабильности ствола Root cause of well-bore instability NPT is является локализованные хрупкие localized fragile zones. Reasons for интервалы. existence are still unclear.
  Данные CDNI были ключом к Time-lapse CDNI data is key to identifying определению причины событий, zones in timely fashion - requires sufficient приведших к непродуктивному времени. resolution from MWD system.
  Методы тщательного контроля и действий Detailed control and contingency measures в нестандартных ситуациях при рисках for drilling risks are now routinely связанных с бурением в настоящее время implemented - planning and execution применяются в рабочем порядке. (real-time) and evaluation phase.
  Имело место значительное уменьшение Significant reduction in NPT exposure for объёма непродуктивного времени для the deep 9 5/8” casing architecture – reduced 9 5/8” обсадных колонн с глубокой посадкой. risk for future development.
  Концентрированное управление рисками Focused risk-management is providing показывает свою ценность через value through improved organizational оптимизированные организационные capability - and winning friends. возможности – и оно завоёвывает все больше сторонников.

## Slide 25: Последующие действия
  Предложено детальное Review of recent 3-D изучение 3-D сейсмики seismic suggested.
  Уточненная геомеханическая Upgrade geomechanical модель (3D модель по model (3D field-wide). месторождению).
  Глубокое азимутальное Near well bore imaging to сканирование стенки better characterize failure скважины. zones.
  Усиление технических Leverage current rig capability возможностей буровой to drill challenging wells установки для бурения with minimum risk/cost. сложных скважин с меньшими рисками и затратами.
  Централизованная поддержки Centralized real-time в реальном времени из decision-support in Ю.-Сахалинска. Yuzhno.
Way Forward
Notes: The next phase of development on Odoptu is likely to benefit significantly from a fully integrated 3-D real-time geomechanics support capability. This will need to incorporate newer vintage seismic from the region.
A 3-D MEM would also incorporate time-lapse LWD image data to track the condition of fragile zones while drilling.
Annular pressure while drilling (APWD) and time-lapse resistivity analysis would permit improved wellbore instability diagnosis for model calibration.
Images from new generation (high-resolution azimuthal) wire-line tools would shed significant light on the near-wellbore stress-state and deformation mechanisms in the weak layers.
To better predict the behaviour of cavity zones, several potential non-regional deformation mechanisms need to be accounted for.